**Appendices**

Appendix 1: Technical Specification

Appendix 2: Technical Offer based on Technical Specifications

Appendix 3: Consultant Questionnaire

Appendix 4: Detailed Pricing Matrix

Appendix 5: The AHA Centre’s Good Business Regulations

# **Appendix 1 :**

# **Scope of Works**

Table below explains objectives, tasks and outputs of this assignment:

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **Deliverable** | **Timeline** | **Payment %** |
| 1 | Inception report, including workplan, methodology, and timeline of the consultancy. | 2 (two) weeks after signing contract | 10% upon received and approved by the AHA Centre |
| 2 | Submission of the first draft of the Crisis Communication manual | Maximum 4th week of July | - |
| 3 | Submission of the second draft (revised) of the Crisis Communication manual after receiving input from the AHA Centre. | Maximum 4th week of August 2023 | 15% upon received and approved by the AHA Centre |
| 4 | Submission of the first draft of the training curriculum for the crisis communication and utilisation of social media for disaster management. | Maximum 3rd week of September 2023 | - |
| 5 | Submission of the second draft (revised) of the Crisis Communication manual after receiving input from the AHA Centre | Maximum 4th week of October 2023 | 15% upon received and approved by the AHA Centre |
| 6 | Submission of the workshop report for the AHA Centre staff on Crisis Communication and social media, including workshop materials, attendance list, participants’ feedback, and event documentation. | Maximum 2nd week of November 2023 | 15% upon received and approved by the AHA Centre |
| 7 | Submission of the training report for the NDMOs’ Communication Focal Points, including training materials, attendance list, participants’ feedback, and event documentation. | Maximum 1st week of December 2023 | 15% upon received and approved by the AHA Centre |
| 8 | Submission of the **Final Summary Report** on the overall consultancy service provided, incorporating evaluation results, lessons learned, and recommendations for the improvement of the programme. | No later than 3rd week of November 2023 | 30% upon received and approved by the AHA Centre |

The due dates for all deliverables will be finalised by the Consulting Agency with the AHA Centre prior to the submission of the inception report.

# **Appendix 2 :**

# **Technical Offer Based On Technical Specification**

| **The AHA Centre Requirements (Minimum)** | **Consultant’s Offer** |
| --- | --- |
| 1. A firm or agency with experience in communication-related fields and proven track records in designing and developing communication manuals/guidelines/documents, course/training curriculum and its materials, preferably with a previous ASEAN project engagement;
 |  |
| 1. The team leader of the consultancy group/institution shall be an experienced expert/researcher/academia with vast experience in designing and developing the abovementioned subjects within ASEAN context, and preferably from ASEAN nationality;
 |  |
| 1. The consultancy group/institution shall provide their past products and portfolios (at least 5 [five] year experience) in designing and developing the abovementioned subjects based on adult learning approaches and methodologies;
 |  |
| 1. Experienced in facilitating workshops with group of experts from diverse backgrounds, including language, culture and organisational system. The personnel of the consultant group/institution are expected to uphold principles of objectivity, integrity and free of conflicts of interest with the AHA Centre and ASEAN.
 |  |
| 1. Experienced working in disaster management, humanitarian, and development will be an advantage;
 |  |
| 1. Excellent written and verbal communication skills in English, a sample of publications/report will be required.
 |  |

***Please provide additional sheets as necessary to include photos and proposed technical specifications (brochures)if any***

# **Appendix 3:**

# **Consultant Questionnaire**

**Publication Reference: AHA-T/2023/May/T-004 – Re Advertise**

|  |  |
| --- | --- |
| Company Name: |  |
| Company Address: |  |
| Contact Name: |  |
| Contact Position / Title: |  |
| Contact Details (Phone / Email): |  |

|  |
| --- |
| **Company Information:** |
| **1** | Is your company registered in Indonesia?**Please provide a copy of Registration.** |  |
| **1a** | **If not**, where is your company registered? |  |
| **2** | When was it registered? |  |
| **3** | Is your company part of an international company? |  |
| **4** | Do you have other offices / plants in the country? Where? |  |
| **5** | How many employees work for your company in-country? |  |
| **Financial Information:** |
| **6** | What is your yearly income in USD over the last 2 years? |  |
| **6a** | Last Year (2022): |  |
| **6b** | Previous Year (2021): |  |
| **7** | Can you provide audited Financial accounts upon request? |  |
| **Customer References:** |
| **8** | Have you worked in the past with the AHA Centre (detail year and activity)? *If yes, please provide details below* |  |
| **8a** |

|  |  |  |
| --- | --- | --- |
| Title Of Contract | Year | Amount (USD) |
|  |  |  |
|  |  |  |

 |
| **9** | Please provide names and contacts of 3 customers to whom you have recently provided the same kind of products/services with a similar value of contract | **1.****2.****3.** |
| **9a** |

|  |  |  |  |
| --- | --- | --- | --- |
| Customer(company) Name | Contact Name | Address | Contact No & Email |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

 |
| **Technical Capacity:** |
| **10** | What is your core activity? |  |
| **11** | What other products / services do you offer? |  |
| **12** | Are you the manufacturer of the products presented in the offer? |  |
| **12a** | If yes: where is the manufacturing site located? |  |
| **12b** | If no, are you an official reseller of these products? Please provide a copy of Dealer Registration. |  |
| **13** | Do you currently have stocks? |  |
| **13a** | If yes, where are they located |  |
| **Delivery Capacity:** |
| **14** | Can you hold dedicated stocks for your customers? |  |
| **15** | Can you manage delivery to the Warehouse delivery locations? |  |
| **16** | What is your average lead time for delivery to the designated locations after receipt of the AHA Centre Purchase Order/Contract? |  |
| **17** | Do you have your own trucks / drivers for delivery? |  |
| **17a** | If not, how will you deliver the items to the designated delivery location? |  |
| **17b** | If you have a designated transport company, please provide the name and address and contact number |  |
| **Financial Conditions:** |
| **18** | What is the validity of your offer? (minimum 60 days) |  |
| **19** | If you get awarded the contract, will you offer fixed prices for 4 months? |  |
| **20** | Do you have an official receipt or invoice? |  |

# **Appendix 4:**

# **Detailed Pricing Matrix**

|  |
| --- |
| Consultant Name: |
| Address: |
| Telephone: |
| Fax: |
| Website: |
| Contact Person: |
| Telephone/Mobile Phone: |
| Email: |
| **ITEM****(Specification as detailed on Appendix 1 & 2)** | **Qty (Percentage)** | **UoM** | **UNIT PRICE (USD)** | **TOTAL PRICE (USD)** | **DELIVERY TIME****(days)\*** |
| 1.Inception report, including workplan, methodology, and timeline of the consultancy. | 10% |  |  |  |  |
| 2.Submission of the first draft (revised) of the Crisis Communication manual after receiving input from the AHA Centre. | 15% |  |  |  |  |
| 3.Submission of the second draft (revised) of the Crisis Communication manual after receiving input from the AHA Centre | 15% |  |  |  |  |
| 4.Submission of the workshop report for the AHA Centre staff on Crisis Communication and social media, including workshop materials, attendance list, participants’ feedback, and event documentation. | 15% |  |  |  |  |
| 5.Submission of the training report for the NDMOs’ Communication Focal Points, including training materials, attendance list, participants’ feedback, and event documentation. | 15% |  |  |  |  |
| 6.Submission of the Final Summary Report on the overall consultancy service provided, incorporating evaluation results, lessons learned, and recommendations for the improvement of the programme. | 30% |  |  |  |  |
| Total amount before VAT |  |  |  |  |  |
| **TAX (USD)***(Including VAT, Withholding Tax, and Any Other Taxes, If Any)* |  |  |
| **GRAND TOTAL (USD)** |  |

All other information that we have not provided automatically implies our full compliance with the requirements, terms and conditions of this tender.

*[Name and Signature of the Consultant’s Authorized Person]*

*[Designation]*

*[Date]*

A**ppendix 5:**

# **The AHA Centre’s Goods Business Regulations**

**These Good Business Regulations are the ground for a professional working relationship between the AHA Centre and the Tenderer.**

**They are general regulations valid unless other particular conditions are mentioned in the contract**. **In case of conflicting terms within documents, the conditions of the contract or tender dossier will prevail on these Good Business Regulations.**

**These Good Business Regulations are the ground for a professional working relationship between the AHA Centre and the Tenderer.**

**They are general regulations valid unless other particular conditions are mentioned in the contract**. **In case of conflicting terms within documents, the conditions of the contract or tender dossier will prevail on these Good Business Regulations.**

**These Good Business Regulations are the ground for a professional working relationship between the AHA Centre and the Tenderer.**

**They are general regulations valid unless other particular conditions are mentioned in the contract**. **In case of conflicting terms within documents, the conditions of the contract or tender dossier will prevail on these Good Business Regulations.**

**These Good Business Regulations are the ground for a professional working relationship between the AHA Centre and the Tenderer.**

**They are general regulations valid unless other particular conditions are mentioned in the contract**. **In case of conflicting terms within documents, the conditions of the contract or tender dossier will prevail on these Good Business Regulations.**

**These Good Business Regulations are the ground for a professional working relationship between the AHA Centre and the Tenderer.**

**They are general regulations valid unless other particular conditions are mentioned in the contract**. **In case of conflicting terms within documents, the conditions of the contract or tender dossier will prevail on these Good Business Regulations.**

**These Good Business Regulations are the ground for a professional working relationship between the AHA Centre and the Tenderer.**

**They are general regulations valid unless other particular conditions are mentioned in the contract**. **In case of conflicting terms within documents, the conditions of the contract or tender dossier will prevail on these Good Business Regulations.**

**These Good Business Regulations are the ground for a professional working relationship between the AHA Centre and the Tenderer.**

**They are general regulations valid unless other particular conditions are mentioned in the contract**. **In case of conflicting terms within documents, the conditions of the contract or tender dossier will prevail on these Good Business Regulations.**

**These Good Business Regulations are the ground for a professional working relationship between the AHA Centre and the Tenderer.**

**They are general regulations valid unless other particular conditions are mentioned in the contract**. **In case of conflicting terms within documents, the conditions of the contract or tender dossier will prevail on these Good Business Regulations.**

**I. Principles of the procurement procedures**

The AHA Centre has transparent procedures to award markets. Essential principles are

* *Transparency* in the procurement process
* *Proportionality* between the procedures followed for awarding contracts and the value of the markets
* *Equal treatment* of potential Consultants

Usual criteria for selecting a consultant are:

* Authorisation to perform the market
* Financial and economic capacities
* Technical expertise
* Professional capacities

Usual criteria to award markets are:

* Automatic award (the cheapest offer complying with all requirements)
* Best value for money (price/quality ratio)

**II. Misbehaviour, ineligibility and exclusion**

**The AHA Centre considers the following misbehaviour as a valid ground for a systematic exclusion of an awarding market procedure and the termination of all working relationships and contracts:**

* **Fraud** defined as any intentional act or omission relating to:
	+ The use or presentation of false, incorrect or incomplete statements or documents, which has as its effect the misappropriation or wrongful retention of the AHA Centre or institutional donors’ funds
	+ Non-disclosure of information, with the same effect
	+ The misapplication of such funds for purposes other than those for which they were originally granted
* **Active corruption**: to deliberately promise or give an advantage to an official for him/her to act or refrain from acting in accordance with his/her duty in a way which damages or is likely to damage the AHA Centre or institutional donors’ financial interests
* **Collusion**: the co-ordination of firm competitive behaviour, with the likely result that prices rise, output is restricted and the profits of the colluding companies are higher than they would otherwise be. Collusive behaviour does not always rely on the existence of explicit agreements between firms, but can also be tacit.
* **Coercive practice:** harming or threatening to harm, directly or indirectly, persons, or their property to influence their participation in a procurement process, or affect the execution of a contract.
* **Bribery**: to offer the AHA Centre employees monetary or in-kind gifts in order to gain additional markets or to continue a contract
* **Involvement in a criminal organisation** or any other **illegal activity** established by a judgement, by the US Government, the European Union, the United Nations or any other donor funding the AHA Centre.
* **Immoral Human Resources practices**: exploitation of child labour and the non-respect of basic social rights and working conditions of employees or sub-Consultants

**The AHA Centre will exclude from a procurement procedure any candidate or tenderer falling into one of the following cases:**

* To be **bankrupt** or to be wound up, to have affairs administered by the courts, to have enter into an arrangement with creditors, to have suspended business activities, to be the subject of proceedings concerning those matters, or are in any analogous situation arising from a similar procedure provided for in national legislation or regulations
* To have been **convicted of an offence** concerning professional conduct by a judgement that has the force of *res judicata*
* To have been **guilty of grave professional misconduct** proven by any means that the AHA Centre can justify
* To have not fulfilled obligations relating to the payment of **social security contributions** or the **payment of taxes** in accordance with the legal provisions of the country in which they are established or with those of the country where the AHA Centre mission is operating or those of the country where the contract is to be performed
* They have been the **subject of a judgement** that has the force of res judicata for fraud, corruption, involvement in a criminal organisation or any other illegal activity detrimental to the Communities' financial interests
* To have been declared to be in **serious breach of contract** for failure to comply with their contractual obligations in another previous procurement procedure

**The AHA Centre will not award contracts to candidates or tenderers who, during the procurement procedure:**

* Are subject to a conflict of interest
* Are guilty of misrepresentation in supplying the information required by the AHA Centre as a condition of participation in the contract procedure or fail to supply this information

**III. Administrative and financial sanctions**

In the event a consultant, candidate or tenderer is engaged in corrupt, fraudulent, collusive or coercive practices, the AHA Centre will impose:

* **Administrative sanctions:**

Administrative sanctions are the official notification of the misconduct to the relevant civil or commercial authorities and the immediate termination of all existing working relationships.

* **Financial sanctions:**

The AHA Centre will request the reimbursement of the cost linked directly and directly to the conduct of a new tendering process or market award. If any, the tender or performance guarantee will be kept by the AHA Centre.

**IV. Information of and access for the Donors**

The AHA Centre will inform immediately the institutional donors and will provide all the relevant information in the event a consultant, candidate or tenderer is engaged in corrupt, fraudulent, collusive or coercive practices.

Furthermore, the Consultants agree to guarantee a right of access to their financial and accounting documents to the representatives of the AHA Centre’s institutional donors for the purposes of checks and audits.

**V. Documents to be a consultant**

Hereafter is the minimal documentation a consultant working with the AHA Centre will have to provide:

* Personnel national id document of the consultant/company representative
* Status and registration of the company
* Mission order or power of attorney authorising the representative to contact

**Important note:** Additional documentation may be required for a particular market.

In addition, the Consultant must have the capacity to issue invoices, receipts and waybills (or delivery notes), to provide a tax clearance certificate and certify documents with an official stamp.

**VI. Anti-Corruption Policy**

If you believe that the action of anyone (or a group of people) working or volunteering for the AHA Centre programs is responsible for violating the above rules, you should file a report through the Whistle-blower Email Hotline.

In order to enable the treatment, reports should give as precise information as possible; your name and contact are optional but encouraged. All reports are treated confidentially to the extent permissible by law.

Note: “***Declaration of compliance & commitment to respect the AHA Centre Good Business Regulations***“ on the next page.

***Declaration of compliance & commitment to respect The AHA Centre Good Business Regulations***

**TO BE FILLED OUT BY THE BIDDER**

I, undersigned …………*representative name……….* representative of …*company name*……… certified that I have read and understood these regulations.

On behalf of the company, I act for, I accept the terms of the AHA Centre Good Business Regulations and I commit to achieve the best performances in the event ………….*company name*………… is awarded a market.

By signing, I certify that ………….*company name*………… has not provided, and will take all reasonable steps to ensure that it does not and will not knowingly provide material support or resources to any individual or entity that commits, attempts to commit, advocates, facilitates, or participates in fraud, active corruption, collusion, coercive practice, bribery, involvement in a criminal organisation or illegal activity, or immoral Human Resources practices, such as the use of Child labour or overriding basic social rights and work conditions or the standards defined by the International Labour Organisation (ILO), particularly in terms of non-discrimination, freedom of association, payment of the legal national minimum wage, no forced labour, and the respect of working and hygiene conditions .

Last, I hereby certify that ………….. *company name* …..……. is not involved in any pending lawsuit, claim or action in the Company’s name, or on behalf of any other person or entity, against the Company, regarding fraud, corruption, bribery or any illegal activity, and has not been convicted guilty of such practices at any time.

All the Consultant’s responsibilities mention in this document extend to any Consultant affiliates and subsidiaries.

Name: Date:

Position: Stamp:

Signature: